## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Elias | Blake | Aidan | Ibrahim | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 6 |  | 0 |  |  |  |  | 0
|  | Design architecture | Project Manager | Elias | 6 |  |  |  |  | 0 |  |  | 0
| Requirements |  |  |  |  | 7 |  | 0 |  |  |  |  | 0
|  | Gather | Requirements Engineer | Blake, Elias | 2 |  | 0 | [5 empty] | 0
|  | Analyze | Requirements Engineer | Blake, Elias | 2 |  | 0 | [5 empty] | 0
|  | Specify | Requirements Engineer | Blake, Elias | 3 |  | 0 | [5 empty] | 0
| Documentation |  |  |  |  | 36 |  | 0 |  |  |  |  | 0
|  | Initial Project Roadmap/Iteration Schedule | Project Manager | Elias | 4 |  | 0 |  | 0 |  |  |  | 0
|  | Project Charter | Project Manager | Elias, Blake | 3 |  | 0 |  | 0 |  |  |  | 0
|  | Release Plan | Project Manager | Elias, Blake | 2 |  | 0 | [5 empty] | 0
|  | Requirements Document | Project Manager, Requirements Engineer | Elias Blake | 6 |  | 0 | [5 empty] | 0
|  | Project Plan | Project Manager, Developers | Elias, Blake, Aidan, Ibrahim | 6 |  | 0 | [5 empty] | 0
|  | Architecture Document | Architect | David, Casey | 6 |  | 0 | [5 empty] | 0
|  | Test Report | Tester | Casey, David | 10 |  | 0 | [5 empty] | 0
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Elias, Blake, Aidan, Ibrahim | 3 |  | 0 | [5 empty] | 0
Coding | Design |  |  |  |  | 28 |  | 0 |  |  |  |  | 0
Iteration 1: |  | Basic UI design for front-end | Developer | Elias, Blake | 2 |  | 0 | [5 empty] | 0
| Development |  |  |  |  | 52 |  | 0 |  |  |  |  | 0
|  | Determine technical stack | Developer | Elias, Blake, Aidan | 2 |  | 0 | [5 empty] | 0
|  | Learn development language | Developer | Blake, Aidan | 12 |  | 0 | [5 empty] | 0
|  | Establish local development environment | Developer | Blake, Aidan | 4 |  | 0 | [5 empty] | 0
|  | Write basic REST endpoints | Developer | Blake, Aidan | 10 |  | 0 | [5 empty] | 0
|  | Write basic schedule resolution logic | Developer | Blake, Aidan | 12 |  | 0 | [5 empty] | 0
|  | Determine data permanence, storage | Developer | Blake, Aidan | 4 |  | 0 | [5 empty] | 0
|  | Basic UI design for front-end | Developer | Aidan, Ibrahim | 2 |  | 0 | [5 empty] | 0
|  | Documentation | Developer | Ibrahim | 2
|  | Unit Testing | Developer | Ibrahim | 4 |  | 0 | [5 empty] | 0
| Analysis |  |  |  |  | 8 |  | 0 |  |  |  |  | 0
|  | System Testing | Tester | Blake, Elias | 2 |  | 0 | [5 empty] | 0
|  | Bug fix as required | Tester, Developer | Elias, Blake, Aidan, Ibrahim | 4 |  | 0 | [5 empty] | 0
|  | Evaluate needs for next iteration | Project Manager | Elias, Blake | 2 |  | 0 | [5 empty] | 0
Iteration 2: | Design |  |  |  |  | 10 |  | 0 |  |  |  |  | 0
|  | Refine UI design, improvements | Project Manager | Elias, Blake | 2 |  | 0 | [5 empty] | 0
|  | Risk analysis | Project Manager | Elias, Blake | 2 |  | 0 | [5 empty] | 0
|  | Find abstraction for scheduling logic | Developer | Elias, Blake | 4 |  | 0 | [5 empty] | 0
|  | Storage/retrieval system for scheduling | Developer | Elias, Blake | 2 |  | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
| Development |  |  |  |  | 23 |  | 0 |  |  |  |  | 0
|  | Review requirements | Developer | Blake, Aidan | 2 |  | 0 | [5 empty] | 0
|  | Login and Logout logic | Developers | Aidan | 3 |  | 0 | [5 empty] | 0
|  | Refine scheduling logic over improved representation | Developer | Blake, Aidan | 5 |  | 0 | [5 empty] | 0
|  | Storage logic between application and front-end | Developer | Blake, Aidan | 6 |  | 0 | [5 empty] | 0
|  | UI Refinements | Developer | Aidan, Ibrahim | 3 |  | 0 | [5 empty] | 0
|  | Documentation | Developer | Ibrahim | 2
|  | Unit Testing | Developer | Ibrahim | 2 |  | 0 | [5 empty] | 0
| Analysis |  |  |  |  | 8 |  | 0 |  |  |  |  | 0
|  | System Testing | Tester | Blake, Elias | 2 |  | 0 | [5 empty] | 0
|  | Bug fix as required | Tester, Developer | Elias, Blake, Aidan, Ibrahim | 4 |  | 0 | [5 empty] | 0
|  | Evaluate needs for next iteration | Project Manager | Elias, Blake | 2 |  | 0 | [5 empty] | 0
Iteration 3: | Design |  |  |  |  | 10 |  | 0 |  |  |  |  | 0
|  | Finalize UI design refinements | Project Manager | Elias, Blake | 3 |  | 0 | [5 empty] | 0
|  | Risk analysis | Project Manager | Elias, Blake | 2 |  | 0 | [5 empty] | 0
|  | Reactive UI | Developer | Aidan, Ibrahim | 3 |  | 0 | [5 empty] | 0
|  | Discuss, Refine Reach Goals | Project Manager | Elias, Blake | 2 |  | 0 | [5 empty] | 0
| Development |  |  |  |  | 24 |  | 0 |  |  |  |  | 0
|  | Review requirements | Developer | Blake, Aidan | 2 |  | 0 | [5 empty] | 0
|  | Finalize UI implementation, Reactive Design | Developer | Aidan, Ibrahim | 10 |  | 0 | [5 empty] | 0
|  | Schedule representation and printing | Developer | Blake, Aidan | 5 |  | 0 | [5 empty] | 0
|  | Final documentation | Developer | Ibrahim | 4 |  | 0 | [5 empty] | 0
|  | Unit Testing | Developer | Ibrahim | 3 |  | 0 | [5 empty] | 0
| Analysis |  |  |  |  | 5 |  | 0 |  |  |  |  | 0
|  | Acceptance Testing | Tester, Project Manager | Blake, Elias | 3 |  | 0 | [5 empty] | 0
|  | Bug fix as required | Tester, Developer | Elias, Blake, Aidan, Ibrahim | 2 |  | 0 | [5 empty] | 0
Total |  |  |  |  | 195 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0