## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Elias | Aiden | Ibrahim | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 6 |  | 2 | 2 | 0 | 0 | 2
|  | Design architecture | Project Manager | Elias | 6 |  | 2 |  | 2 |  |  | 2
| Requirements |  |  |  |  | 7 |  | 3 | 3 | 0 | 0 | 3
|  | Gather | Requirements Engineer | Elias | 2 |  | 1 |  | 1 |  |  | 1
|  | Analyze | Requirements Engineer | Elias | 2 |  | 0.5 |  | 0.5 |  |  | 0.5
|  | Specify | Requirements Engineer | Elias | 3 |  | 1.5 |  | 1.5 |  |  | 1.5
| Documentation |  |  |  |  | 47 |  | 68.9 | 9.9 | 0 | 59 | 68.9
|  | Initial Project Roadmap/Iteration Schedule | Project Manager | Elias | 4 |  | 3.5 |  | 3.5 |  |  | 3.5
|  | Project Charter | Project Manager | Elias, Ibrahim | 10 |  | 3.5 |  | 3.5 |  | 0 | 3.5
|  | Release Plan | Project Manager | Elias | 2 |  | 0 |  |  |  |  | 0
|  | Requirements Document | Project Manager, Requirements Engineer | Elias, Ibrahim | 6 |  | 21.2 |  | 1.2 |  | 20 | 21.2
|  | Project Plan | Project Manager, Developers | Elias, Aiden, Ibrahim | 6 |  | 26.5 |  | 1.5 | 0 | 25 | 26.5
|  | Architecture Document | Architect | Elias, Ibrahim | 6 |  | 14.2 |  | 0.2 |  | 14 | 14.2
|  | Test Report | Tester | Elias, Ibrahim, Aiden | 10 |  | 0 |  |  |  |  | 0
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Elias, Aiden, Ibrahim | 3 |  | 0 |  |  |  |  | 0
Iteration 1: | Design |  |  |  |  | 2 |  | 0.2 | 0.2 | 0 | 0 | 0.2
|  | Basic UI design for front-end | Developer | Elias | 2 |  | 0.2 |  | 0.2 |  |  | 0.2
| Development |  |  |  |  | 52 |  | 9.66 | 9.46 | 0.1 | 0.1 | 9.66
|  | Determine technical stack | Developer | Aiden, Elias | 2 |  | 0.3 |  | 0.1 | 0.1 | 0.1 | 0.3
|  | Learn development language | Developer | Aiden, Elias | 12 |  | 0.1 |  | 0.1 | 0 |  | 0.1
|  | Establish local development environment | Developer | Aiden, Elias | 4 |  | 0.96 |  | 0.96 | 0 |  | 0.96
|  | Write basic REST endpoints | Developer | Aiden, Elias | 10 |  | 3.1 |  | 3.1 | 0 |  | 3.1
| *SPIKED ISSUE* | Write basic schedule resolution logic | Developer | Aiden, Elias | 12 |  | 3 |  | 3 | 0 |  | 3
|  | Determine data permanence, storage | Developer | Aiden, Elias | 4 |  | 1.1 |  | 1.1 | 0 |  | 1.1
|  | Basic UI implementation for front-end | Developer | Aiden, Elias, Ibrahim | 2 |  | 0.9 |  | 0.9 | 0 | 0 | 0.9
| *CARRY OVER* | Documentation | Developer | Elias, Ibrahim | 2 |  | 0.2 |  | 0.2 |  | 0 | 0.2
| *CARRY OVER* | Unit Testing | Developer | Elias | 4 |  | 0 |  | 0 |  |  | 0
| Analysis |  |  |  |  | 8 |  | 1.5 | 1.5 | 0 | 0 | 1.5
|  | System Testing | Tester | Elias | 2 |  | 1 |  | 1 |  |  | 1
|  | Bug fix as required | Tester, Developer | Elias, Aiden, Ibrahim | 4 |  | 0 |  | 0 | 0 | 0 | 0
|  | Evaluate needs for next iteration | Project Manager | Elias | 2 |  | 0.5 |  | 0.5 |  |  | 0.5
Iteration 2: | Design |  |  |  |  | 10 |  | 1.1 | 0 | 0.1 | 1 | 1.1
|  | Refine UI design, improvements | Project Manager | Elias, Aiden, Ibrahim | 2 |  | 0 |  | 0 | 0 | 0 | 0
|  | Risk analysis | Project Manager | Elias, Ibrahim, Aiden | 2 |  | 1.1 |  | 0 | 0.1 | 1 | 1.1
|  | Find abstraction for scheduling logic | Developer | Elias, Aiden | 4 |  | 0 |  | 0 | 0 |  | 0
|  | Storage/retrieval system for scheduling | Developer | Elias | 2 |  | 0 |  | 0 |  |  | 0
| Development |  |  |  |  | 44 |  | 7.5 | 7.5 | 0 | 0 | 7.5
|  | Review requirements | Developer | Elias | 2 |  | 1.5 |  | 1.5 |  |  | 1.5
|  | Port rust prototype to Python | Developer | Aiden | 10 |  | 0 |  |  | 0 |  | 0
|  | Login and Logout logic | Developers | Aiden, Elias | 3 |  | 1 |  | 1 | 0 |  | 1
|  | Research schedule resolution proble and logic | Developers | Elias, Aiden | 10 |  | 5 |  | 5 | 0 |  | 5
|  | Time tabling/scheduling logic MVP | Developer | Elias, Aiden | 10 |  | 0 |  | 0 | 0 |  | 0
|  | Implement UI Refinements | Developer | Aiden, Elias, Ibrahim | 3 |  | 0 |  | 0 | 0 |  | 0
|  | Project CI/CD | Developer | Elias, Aiden | 2 |  | 0 |  | 0 | 0 | 0 | 0
| *CARRY OVER* | Documentation | Developer | Elias, Aiden | 2 |  | 0 |  | 0 | 0 |  | 0
| *CARRY OVER* | Unit Testing | Developer | Elias, Aiden | 2 |  | 0 |  | 0 | 0 |  | 0
| Analysis |  |  |  |  | 8 |  | 0 | 0 | 0 | 0 | 0
|  | System Testing | Tester | Elias | 2 |  | 0 |  | 0 |  |  | 0
|  | Bug fix as required | Tester, Developer | Elias, Aiden, Ibrahim | 4 |  | 0 |  | 0 | 0 | 0 | 0
|  | Evaluate needs for next iteration | Project Manager | Elias | 2 |  | 0 |  | 0 |  |  | 0
Iteration 3: | Design |  |  |  |  | 8 |  | 5 | 5 | 0 | 0 | 5
|  | Refine UI design, improvements | Project Manager | Elias, Aiden, Ibrahim | 2 |  | 0 |  | 0 |  |  | 0
| *CARRY OVER* | Find abstraction for scheduling logic | Developer | Elias, Aiden | 4 |  | 5 |  | 5 |  |  | 5
| *CARRY OVER* | Storage/retrieval system for scheduling | Developer | Elias | 2 |  | 0 |  | 0 |  |  | 0
| Development |  |  |  |  | 42 |  | 25 | 25 | 0 | 0 | 25
| *CARRY OVER* | Port rust prototype to Python | Developer | Aiden | 10 |  | 0 |  |  | 0 |  | 0
| *CARRY OVER* | Login and Logout logic | Developers | Aiden, Elias | 3 |  | 0 |  | 0 | 0 |  | 0
| *CARRY OVER* | Research schedule resolution proble and logic | Developers | Elias, Aiden | 10 |  | 5 |  | 5 | 0 |  | 5
| *CARRY OVER* | Time tabling/scheduling logic MVP | Developer | Elias, Aiden | 10 |  | 20 |  | 20 | 0 |  | 20
| *CARRY OVER* | Implement UI Refinements | Developer | Aiden, Elias, Ibrahim | 3 |  | 0 |  | 0 | 0 |  | 0
| *CARRY OVER* | Project CI/CD | Developer | Elias, Aiden | 2 |  | 0 |  | 0 | 0 | 0 | 0
| *CARRY OVER* | Documentation | Developer | Elias, Aiden | 2 |  | 0 |  | 0 | 0 |  | 0
| *CARRY OVER* | Unit Testing | Developer | Elias, Aiden | 2 |  | 0 |  | 0 | 0 |  | 0
| Analysis |  |  |  |  | 8 |  | 0 | 0 | 0 | 0 | 0
|  | System Testing | Tester | Elias | 2 |  | 0 |  | 0 |  |  | 0
|  | Bug fix as required | Tester, Developer | Elias, Aiden, Ibrahim | 4 |  | 0 |  | 0 | 0 | 0 | 0
|  | Evaluate needs for next iteration | Project Manager | Elias | 2 |  | 0 |  | 0 |  |  | 0
Iteration 4: | Design |  |  |  |  | 20 |  | 0 | 0 | 0 | 0 | 0
|  | Refine UI design, improvements | Project Manager | Elias, Aiden, Ibrahim | 2 |  | 0 |  |  |  |  | 0
|  | refinements for scheduling data models | Developer | Elias, Aiden | 8 |  | 0 |  |  |  |  | 0
|  | refinements for scheduling logic | Developer | Elias, Aiden | 8 | [6 empty] | 0
| *CARRY OVER* | Storage/retrieval system for scheduling | Developer | Elias | 2 |  | 0 |  |  |  |  | 0
| Development |  |  |  |  | 94 |  | 0 | 0 | 0 | 0 | 0
|  | Refine constraint data types | Developer | Elias, Aiden | 10 |  | 0 |  |  |  |  | 0
|  | Refine class data type | Developer | Elias, Aiden | 6 |  | 0 |  |  |  |  | 0
|  | Refine instructor data type | Developer | Elias, Aiden | 6 |  | 0 |  |  |  |  | 0
|  | Refine time data types | Developer | Elias, Aiden | 8 |  | 0 |  |  |  |  | 0
|  | Refine schedule data types | Developer | Elias, Aiden | 10 |  | 0 |  |  |  |  | 0
|  | Teaching load logic | Developer | Elias, Aiden | 6 |  | 0 |  |  |  |  | 0
|  | Meeting days logic | Developer | Elias, Aiden | 6 |  | 0 |  |  |  |  | 0
|  | Time slot logic | Developer | Elias, Aiden | 10 |  | 0 |  |  |  |  | 0
|  | Day logic | Developer | Elias, Aiden | 10 |  | 0 |  |  |  |  | 0
| *CARRY OVER* | Port rust prototype to Python | Developer | Aiden | 10 |  | 0 |  |  |  |  | 0
| *CARRY OVER* | Login and Logout logic | Developers | Aiden, Elias | 3 |  | 0 |  |  |  |  | 0
| *CARRY OVER* | Implement UI Refinements | Developer | Aiden, Elias, Ibrahim | 3 |  | 0 |  |  |  |  | 0
| *CARRY OVER* | Project CI/CD | Developer | Elias, Aiden | 2 |  | 0 |  |  |  |  | 0
| *CARRY OVER* | Documentation | Developer | Elias, Aiden | 2 |  | 0 |  |  |  |  | 0
| *CARRY OVER* | Unit Testing | Developer | Elias, Aiden | 2 |  | 0 |  |  |  |  | 0
| Analysis |  |  |  |  | 8 |  | 0 | 0 | 0 | 0 | 0
|  | System Testing | Tester | Elias | 2 |  | 0 |  |  |  |  | 0
|  | Bug fix as required | Tester, Developer | Elias, Aiden, Ibrahim | 4 |  | 0 |  |  |  |  | 0
|  | Evaluate needs for next iteration | Project Manager | Elias | 2 |  | 0 |  |  |  |  | 0
Total |  |  |  |  | 242 | 242 | 123.86 | 123.86 | 63.56 | 0.2 | 60.1 | 123.86